CBIS-DDSM (Curated Breast Imaging Subset of DDSM)

INbreast

VinDr-Mammo

SECOND LOOK — 12-Week Prototype Checklist (TF Lite, On-Device)

Goal: Deliver a working, privacy-preserving mobile or browser prototype in 3 months that:

• Accepts a mammogram image or photo
• Performs on-device inference using TF Lite
• Highlights regions of interest
• Produces a coarse concern tier
• Provides conservative, non-diagnostic guidance
• Stores nothing and transmits nothing

If it runs offline on a real device, you win.

TEAM ROLES (Assign in Week 1)

Each student owns one domain but everyone reviews everything.

Deployment Lead (TF Lite Owner)
Controls model export, conversion, quantization, performance, and runtime integration.
If the model does not convert → it does not ship.

Modeling Lead
Owns preprocessing, augmentation, training, calibration, and evaluation.

App & UX Lead
Owns interface, disclaimer gate, image capture, visualization, and privacy behavior.

Rotate peer review weekly. Silent failure is the natural predator of student teams.

PHASE 1 — DATA & PIPELINE FOUNDATION

Weeks 1–3

Checklist

☐ Select primary training dataset (CBIS-DDSM recommended)
☐ Select secondary dataset for external validation (INbreast or VinDr-Mammo)
☐ Document licenses and usage constraints
☐ Build dataset intake pipeline (download → parse → normalize)
☐ Convert images to standardized format (size, grayscale, orientation)
☐ Extract region labels if available
☐ Define mapping from dataset labels → concern tiers (Low / Moderate / Elevated)
☐ Create dataset cards documenting biases, limitations, and label meaning
☐ Split data into train/validation/test with fixed seeds
☐ Produce first small working subset for rapid iteration

Deliverables (end of Week 3)

✔ Reproducible “Data Build” script
✔ Clean tensor dataset ready for training
✔ Dataset cards
✔ Label-to-tier mapping document

PHASE 2 — BASELINE MODELS

Weeks 4–5

Goal: Establish sanity before deep learning heroics.

Checklist

☐ Build simple baseline classifiers using extracted features or embeddings
☐ Implement logistic regression / random forest baseline
☐ Define evaluation metrics (AUROC, precision/recall, calibration)
☐ Create confusion matrices and error analysis
☐ Select one lightweight CNN backbone compatible with TF Lite
☐ Train first end-to-end image model
☐ Save checkpoints in TensorFlow SavedModel format
☐ Establish fixed evaluation protocol

Deliverables (end of Week 5)

✔ Baseline metrics report
✔ Model selection rationale
✔ Locked evaluation pipeline

Remember: a dumb baseline that works beats a brilliant model that can’t ship.

PHASE 3 — ROBUSTNESS TO REAL-WORLD PHOTOS

Weeks 6–7

This is the difference between “academic demo” and “actual product.”

Checklist

☐ Implement augmentation simulating consumer capture artifacts:

• Glare and reflections
• Perspective distortion
• Motion blur
• Compression artifacts
• Partial occlusion
• Brightness/contrast extremes
• Screen moiré patterns

☐ Train model with augmented data
☐ Develop image quality scoring system
☐ Implement “unusable image” detection
☐ Write retake guidance instructions aligned with model tolerance

Deliverables (end of Week 7)

✔ Augmentation module
✔ Image quality gate
✔ Photo-capture guidance materials

If the model happily analyzes a photo of a toaster, you have failed.

PHASE 4 — EXPLAINABILITY & SAFE LANGUAGE

Week 8

Checklist

☐ Implement heatmap or saliency visualization
☐ Validate that highlighted regions correspond to known labels
☐ Design non-diagnostic explanation templates
☐ Add uncertainty-aware phrasing
☐ Create forbidden-phrase list (no diagnostic claims)
☐ Build automated text checks for prohibited language

Deliverables

✔ Explanation specification
✔ Approved text library
✔ Heatmap overlay working on sample images

The system points. It does not pronounce.

PHASE 5 — TF LITE DEPLOYMENT PIPELINE

Weeks 9–10

This is where many teams perish.

Checklist

☐ Export trained model to TensorFlow SavedModel
☐ Convert to TF Lite format
☐ Apply FP16 quantization (minimum requirement)
☐ Test inference correctness vs original model
☐ Benchmark speed and memory on target device
☐ Implement deterministic preprocessing identical to training
☐ Validate no unsupported operations remain
☐ Build regression test (known input → known output)

Optional (only if stable):

☐ Attempt INT8 quantization using representative dataset

Deliverables

✔ TF Lite model file
✔ Conversion script
✔ Performance report
✔ On-device inference demo

If conversion fails, simplify the model. Reality always wins.

PHASE 6 — APPLICATION & UX

Weeks 10–11 (overlaps with Phase 5)

Required Flow

Disclaimer Gate → Upload/Capture → Scanning → Results Viewer

Checklist

☐ Implement mandatory disclaimer acceptance
☐ Build image upload or camera capture interface
☐ Integrate TF Lite inference
☐ Display heatmap overlays with pan/zoom
☐ Show concern tier with explanation
☐ Provide retake guidance when quality is poor
☐ Include professional follow-up recommendation
☐ Embed required branding text and logo
☐ Ensure readable, calm visual design
☐ No login, no storage, no analytics

Deliverables

✔ Clickable prototype
✔ Functional end-to-end app
✔ Usability pass for clarity and anxiety reduction

“Medical-grade calm” beats Silicon Valley neon optimism.

PHASE 7 — VERIFICATION & VALIDATION

Week 11–12

Checklist

☐ Unit tests for preprocessing pipeline
☐ Deterministic inference tests
☐ Stress tests with distorted inputs
☐ External validation on independent dataset
☐ Document performance degradation on photo artifacts
☐ Verify graceful failure modes
☐ Compile model card and limitations document

Deliverables

✔ Validation report
✔ Model card
✔ Known limitations summary

A model without limitations documentation is just a rumor.

PHASE 8 — PRIVACY & SECURITY PROOF

Week 12

Checklist

☐ Confirm no image data is transmitted during analysis
☐ Disable analytics or telemetry
☐ Document network behavior
☐ Verify images are not persisted locally
☐ Provide user export option only by explicit action
☐ Write privacy statement
☐ Create simple network monitoring test

Deliverables

✔ Privacy/security documentation
✔ Technical proof notes
✔ Network audit script

Trust requires evidence, not promises.

PHASE 9 — OPEN-SOURCE READINESS

Final Week

Checklist

☐ Organize repo structure:

data_pipeline/
modeling/
tflite_deployment/
app/

☐ Include reproducible training scripts
☐ Provide environment setup instructions
☐ Add license (MIT or Apache)
☐ Write CONTRIBUTING guide
☐ Document full train → export → deploy workflow

Deliverables

✔ Clean public repo
✔ Reproducibility documentation
✔ Release checklist

Future researchers should not need a séance to run your code.

SUCCESS CRITERIA (END OF MONTH 3)

You have succeeded if:

✔ A user can load the app
✔ Provide an image or photo
✔ The model runs entirely on device
✔ Regions of interest are highlighted
✔ A coarse concern tier is displayed
✔ Guidance text is shown
✔ No data leaves the device